- Marketing Campaign Planning

- Review Business Strategy Landscape

- Identify service/product gaps and opportunities

- Complete SWOT analysis

- Review business model

- Review organizational marketing strategy

- Review local marketing strategy

- Review global marketing strategy

- Review marketing plan for campaign budget

- Establish go-to-markets for organization

- Evaluate alignment to corporate strategy goals

- Evaluate competitive advantages

- Review product and service margins

- Review previous campaign performance

- Business Strategy Landscape Review Complete

- Develop Campaign Concepts

- Create process for qualifying ideas

- Establish process for idea sharing

- Gather ideas

- Final shaping and development of ideas

- Research market environment

- Develop preliminary campaign concepts

- Identify campaign targets

- Develop campaign success metrics

- Develop campaign tracking and analysis process

- Validate concepts through test groups and market research

- Establish campaign focus list

- Establish campaign categories

- Develop public relations strategy

- Establish preliminary ideal campaign timing for promotion

- Determine organization regional campaigns

- Determine organization global campaigns

- Determine organization country campaigns

- Identify localization requirements

- Campaign Concepts Complete

- Create Localization Strategy

- Review corporate sales objectives

- Review regional business models

- Review global/country business models

- Review marketing objectives

- Review marketing plan

- Establish campaign opportunities

- Review services and product mix and forecast

- Review product release cycles

- Determine campaign mix for each region

- Determine campaign success measures for each region

- Determine tracking mechanism

- Create localization strategy

- Localization Strategy Complete

- Communicate and Train Internal Organization

- Establish corporate internal communications process

- Determine regional and country division communications process

- "Plan communications methods, logistics, and timing"

- "Regional and country communications to sales, marketing, and management"

- Determine internal systems to respond to campaign

- Create communications plan

- Identify internal training requirements

- Develop internal training

- Organization Internal Communications and Training Complete

- Customer Relationship Management

- Review customer data and feedback

- Review company segments and channels

- Identify targets for each campaign

- Segment data for each campaign

- Prepare/procure lists for each campaign

- Customer Relationship Management Complete

- Analyze Regional/Global/Country Business Models

- Establish target regions

- Determine local gaps

- Review local competition

- Develop competitive advantage

- Identify go-to partners

- Regional/Global/Country Business Models Complete

- Develop Campaign

- Review campaign concepts

- Create campaign list

- Identify campaign leads

- Develop Individual campaigns

- Develop campaign schedules

- Determine calls to action

- Determine advertising/promotion methods and mix

- Campaign Development Complete

- Develop Campaign Creative and Testing

- Select vendor for creative

- Determine campaign voice/messaging style

- Develop concepts and comps

- Select creative for campaign

- Prepare pretest materials

- Pretest campaign

- Determine if pretest creative achieves objectives

- Improve creative based on pretest results

- Campaign Creative and Testing Complete

- Develop Strategy for External Promotions

- Develop promotion strategy

- Develop press releases

- Develop announcements

- Provide pre-release information to analysts

- Generate 'buzz'

- Execute publicity strategy

- Promotion - External Complete

- Production

- Submit campaign material for broadcast publications

- Select vendor for appropriate production methods

- Production of materials

- Dissemination of materials

- Production Complete

- Campaign Release

- Develop campaign release schedules

- Determine release teams

- Perform Inside sales calls

- Execute campaign

- Campaign Release Complete

- Campaign Effectiveness

- Evaluate campaign effectiveness

- Review regional sales

- Review global sales

- Review customer data and feedback

- Perform market analysis

- Review success measures

- Measure campaign effectiveness

- Identify any gaps

- Develop future campaign ideas

- Campaign Effectiveness

- Marketing Campaign Planning Complete